## Earned Value Management
OSINT APPLICATION - EARNED VALUE SHEET
DESCRIPTION | This sheet is tracking the progress of the OSINT application creation followed by the various budgets that the tasks required. The value table performance indicators have been included to identify areas of high spend and achievement. |  |  |  | PREPARED BY | Krish Dhungana | DATE | 2023-12-01
PLANNED VALUE – Given in (USD $) based on estimates of real cost in the Chicago, IL area
WORK BRKDWN STRUCTURE | TASK TITLE | TOTAL BUDGETED COST | PERIOD |  |  |  | Key
|  |  | 1 | 2 | 3 | 4 |  | Monetary High Points | Represent key spendature within the project
1.1 | Baseline Information | 0 | 0 | 0 | 0 | 0 |  | Meeting + Review | Represent periods of review and meeting within the group
1.2 | Initial Meeting | 0 | 0 | 0 | 0 | 0 |  | Major Steps | Represent the major breakdown points of the project
1.3 | API Selection | 0 | 0 | 0 | 0 | 0
1.4 | OSINT Application Preview | 200 | 200 | 0 | 0 | 0 | PERIOD | 4 Week Period - 7 days per period
1.5 | GUI Design Overview | 500 | 250 | 250 | 0 | 0
1.6 | Completetion of OSINT APP | 1200 | 500 | 700 | 0 | 0
2.1 | Work Breakdown Structure (WBS) | 0 | 0 | 0 | 0 | 0
2.2 | GUI Design (Creation) | 1200 | 0 | 800 | 400 | 0
2.3 | Data Retrieval Module | 1500 | 0 | 450 | 1050 | 0
2.4 | Data Processing Module | 800 | 0 | 300 | 500 | 0
2.5 | GUI Integration | 500 | 0 | 200 | 300 | 0
2.6 | OSINT APP GUI Testing | 600 | 0 | 200 | 400 | 0
3.1 | API Performance | 0 | 0 | 0 | 0 | 0
3.2 | Process API Data - URLSCAN | 250 | 0 | 125 | 125 | 0
3.3 | Process API Data - Domain ID | 250 | 0 | 115 | 135 | 0
3.4 | Process API Data - Web Scrapping | 250 | 0 | 0 | 150 | 100
3.5 | Process API Data - GEO - IP | 250 | 0 | 0 | 150 | 100
3.6 | Data Processing Module Review | 0 | 0 | 0 | 0 | 0
4.1 | GUI Integration and Testing | 1500 | 0 | 0 | 400 | 1100
5.1 | Final Meeting + Turn In | 0 | 0 | 0 | 0 | 0
TBC | TOTAL BUDGETED COST | 9000 | 950 | 3140 | 3610 | 1300
PV | CUMLATIVE PLANNED VALUE |  | 950 | 4090 | 7700 | 9000
ACTUAL COST
AC | CUMULATIVE ACTUAL COST |  | 1200 | 4540 | 8250 | 9950
EARNED VALUE
EV | CUMULATIVE EARNED VALUE |  | 8850 | 9000 | 9000 | 9000
PROJECT PERFORMANCE METRICS
CV | COST VARIANCE | ( EV – AC ) | 7650 | 4460 | 750 | -950
SV | SCHEDULE VARIANCE | ( EV – PV ) | 7900 | 4910 | 1300 | 0
CPI | COST PERFORMANCE INDEX | ( EV / AC ) | 7.375 | 1.9824 | 1.0909 | 0.90452
SPI | SCHEDULE PERFORMANCE INDEX | ( EV / PV ) | 9.3158 | 2.2005 | 1.1688 | 1
EAC | ESTIMATED COST AT COMPLETION |  | 1220.339 | 4540 | 8250 | 9950

## Actual Cost Worksheet
EARNED VALUE MANAGEMENT TEMPLATE
ACTUAL COST – Actual cost incurred for each task per period.
WORK BRKDWN STRUCTURE | TASK TITLE | TOTAL BUDGETED COST | PERIOD
|  |  | 1 | 2 | 3 | 4
1.1 | Baseline Information | 0 | 0 | 0 | 0 | 0
1.2 | Initial Meeting | 0 | 0 | 0 | 0 | 0
1.3 | API Selection | 0 | 0 | 0 | 0 | 0
1.4 | OSINT Application Preview | 0 | 200 | 0 | 0 | 0
1.5 | GUI Design Overview | 500 | 250 | 250 | 0 | 0
1.6 | Completetion of OSINT APP | 1700 | 750 | 900 | 0 | 0
2.1 | Work Breakdown Structure (WBS) | 0 | 0 | 0 | 0 | 0
2.2 | GUI Design (Creation) | 100 | 0 | 800 | 400 | 0
2.3 | Data Retrieval Module | 1500 | 0 | 450 | 1050 | 0
2.4 | Data Processing Module | 800 | 0 | 300 | 500 | 0
2.5 | GUI Integration | 500 | 0 | 200 | 300 | 0
2.6 | OSINT APP GUI Testing | 600 | 0 | 200 | 400 | 0
3.1 | API Performance | 0 | 0 | 0 | 0 | 0
3.2 | Process API Data - URLSCAN | 250 | 0 | 125 | 125 | 0
3.3 | Process API Data - Domain ID | 250 | 0 | 115 | 135 | 0
3.4 | Process API Data - Web Scrapping | 250 | 0 | 0 | 150 | 100
3.5 | Process API Data - GEO - IP | 250 | 0 | 0 | 150 | 100
3.6 | Data Processing Module Review | 0 | 0 | 0 | 0 | 0
4.1 | GUI Integration and Testing | 2000 | 0 | 0 | 500 | 1500
5.1 | Final Meeting + Turn In | 0 | 0 | 0 | 0 | 0
AC | ACTUAL COST |  | 1200 | 3340 | 3710 | 1700
| CUMULATIVE ACTUAL COST |  | 1200 | 4540 | 8250 | 9950

## Earned Value Worksheet
EARNED VALUE MANAGEMENT TEMPLATE
CUMULATIVE EARNED VALUE – For each task and the period the completed percentage is shown
WORK BRKDWN STRUCTURE | TASK TITLE | TOTAL BUDGETED COST | PERIOD
|  |  | 1 | 2 | 3 | 4
1.1 | Baseline Information | 0 | 100% | 0% | 0% | 0%
1.2 | Initial Meeting | 0 | 100% | 0% | 0% | 0%
1.3 | API Selection | 0 | 100% | 0% | 0% | 0%
1.4 | OSINT Application Preview | 200 | 100% | 100% | 100% | 100%
1.5 | GUI Design Overview | 500 | 100% | 100% | 100% | 100%
1.6 | Completetion of OSINT APP | 1200 | 100% | 100% | 100% | 100%
2.1 | Work Breakdown Structure (WBS) | 0 | 0% | 100% | 0% | 0%
2.2 | GUI Design (Creation) | 1200 | 100% | 100% | 100% | 100%
2.3 | Data Retrieval Module | 1500 | 100% | 100% | 100% | 100%
2.4 | Data Processing Module | 800 | 100% | 100% | 100% | 100%
2.5 | GUI Integration | 500 | 100% | 100% | 100% | 100%
2.6 | OSINT APP GUI Testing | 600 | 100% | 100% | 100% | 100%
3.1 | API Performance | 0 | 0% | 100% | 100% | 0%
3.2 | Process API Data - URLSCAN | 250 | 100% | 100% | 100% | 100%
3.3 | Process API Data - Domain ID | 250 | 100% | 100% | 100% | 100%
3.4 | Process API Data - Web Scrapping | 250 | 100% | 100% | 100% | 100%
3.5 | Process API Data - GEO - IP | 250 | 100% | 100% | 100% | 100%
3.6 | Data Processing Module Review |  | 0% | 0% | 80% | 90%
4.1 | GUI Integration and Testing | 1500 | 90% | 100% | 100% | 100%
5.1 | Final Meeting + Turn In | 0 | 0% | 0% | 100% | 100%
EV | CUMULATIVE EARNED VALUE |  | 8850 | 9000 | 9000 | 9000